## Task Tracker
Note :- Please do not change application API structure during development and keep adding code files whereever necessary for implementation. GitHub CheckIn should be done after peer-review only.
Task ID | Module | Task Name | Priority | Status | Start Date | Expected Completion | End Date | Remarks / Blocker
CR-001 | WealthAI | WealthAI design document go through. | Low
CR-002 | WealthAI | Create a Gmail Credential for startup | High
CR-003 | WealthAI | Setup GitHub with main & dev branches. | High
CR-004 | WealthAI | Setup local development environment - BOTH | High |  |  |  |  | Will do on screen share together
CR-005 | WealthAI DB | Create postgres database on local using migration script. | High
CR-006 | WealthAI UI | Create a Wealth UI for the portfolio. - Master Prompt Given | High
CR-007 | WealthAI Trade UI | Create a dedicated UI for the trading engine. - Master Prompt Given | High
CR-008 | Bond | Node API CRUD stabilization/import-export. Create common API response structure | High
CR-009 | WealthAI DB | Create postgres database on server using migration script. | High |  |  |  |  | Milestone - 1
CR-010 | WealthAI | Create Staging Environment - Deploy Frontend , Backend and DB | High |  |  |  |  | Milestone - 1
CR-011 | Mutual Funds | Node API CRUD stabilization/import-export. Create API response structure. | Medium
CR-012 | Deposits | Node API CRUD stabilization/import-export. Create API response structure. | Medium
CR-013 | India_market | Node API CRUD stabilization/import-export. Create API response structure. | Medium
CR-014 | auth | Node API CRUD stabilization/import-export. Create API response structure. | Medium
CR-015 | WealthAI DB | Create postgres database on prod server using migration script. | Medium |  |  |  |  | Milestone - 2
CR-016 | WealthAI | Create Production Environment - Deploy Frontend , Backend and DB | Medium |  |  |  |  | Milestone - 2